## Sheet1
COSC1076 ¦ Semester 1 2021
Assignment 2 ¦ Weekly Update Tracking Sheet
Group Name:
Group Member: | A |  | Progress Classes: | Ahead
Group Member: | B |  |  | On-track
Group Member: | C |  |  | Behind
Group Member: | D |  |  | Way Behind
Tutor:
Class:
|  | Week 7 | Goals | Tutor Notes | Indidvidual Updates | A | B | C | D
|  |  | Group Formed |  | Weekly Contribution
|  |  | MS Team created |  | Issues
|  |  | Git Repo created |  | Other Notes
|  | Progress | Way Behind
|  | Week 8 | Goals | Tutor Notes | Indidvidual Updates | A | B | C | D
|  |  | Choice of where to use linked list, vector & array | class diagram, basic implementation of the classes. Game needs to be tested. NEED TO implement loading and gameplay. Need to write | Weekly Contribution | Implemented linked list, node, game, player, board, tile and tilelist classes.
|  |  | Initial Design of ADTs (classes and potential methods) |  | Issues | Getting both templates and inheritance to work with node and linkedlist for a tile implementation. Specifically templating node to take a data variable of any type and then using a tile class that inherits node. Wasn't able to get this to work so we reused the linked list code to make a tile list which stores tiles.
|  |  | Main menu |  | Other Notes | Done
|  |  | User Prompt (for gameplay), but no/minimal error checking |  |  | Done
|  |  | Linked List implementation |  |  | Done
|  |  | Implementation(s) or suitable ADTs wrapper for the use of vector and arrays, game logic not required |  | Issues | Done
ADT implementation for storing information, game loop logic not required
Other Notes
|  | Progress | On-track
|  | Week 9 | Goals | Tutor Notes | Indidvidual Updates |  | B | C | D
|  |  | Load/Save to/from data strucutres (doesn't require integration with main menu or game loop) |  | Xander managed to implement the load and save game functionality whilst I focused on fully implementing the game play and modifying the programs inputs to be robust enough to be capable of EOF and newline handling when using input files.
|  |  | Initialisation of data strctures for new game |  | Issues | Done
|  |  | Write Tests Cases for common uses |  | Other Notes we made contact with our 3rd member Zixun Zhou and asked them to start on the test files. I asked them to meet with us to discuss test cases but they assured me that they would handle the task on their own. | Not Done
|  |  | Gameplay for single round |  |  | Done
|  | Progress | Way Behind
|  | Week 10 | Goals | Tutor Notes | Indidvidual Updates |  | B | C | C
Fully complete implementation and error free
|  |  | Full error checking of user prompt |  | Fully implemented gameplay and EOF handling. The rules were implemented but still very buggy. Still no update from Zixun about the tests.
Fully implement Rules
Final Tests
|  |  | Group Report Written |  | Issues
|  | Progress | Way Behind |  | Other Notes